## 11358_1
General Information:
Serial num: | 11358
Axis num: | 1
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | OK
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | Not OK | Mechanical grinding noise when running. The noise is cyclic linked to the rotation.
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
| Motion Performance | µm
3 | Repeatability | 6.3 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 42 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed.
5. | Switch Performance | µm
5.1 | Low Limit Engage | 40 | OK
5.2 | Low Limit Disengage | 10 | OK
5.3 | High Limit Engage | 10 | OK
5.4 | High Limit Disengage | 20 | OK
6 | Resolver Performance | 20 | OK | Variations over 1 turn

## 11358_2
General Information:
Serial num: | 11358
Axis num: | 2
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | Check | Some Lemo nuts loose
1.1.2 | Observations |  | Not OK | Upper limit switch lever bent
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | Check | Minor scratching/grinding noise and some distcict sounds at in rotation frequency
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
| Motion Performance | µm
3 | Repeatability | 1.8 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 61 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed. | µ
5. | Switch Performance | µm
5.1 | Low Limit Engage | 36 | OK
5.2 | Low Limit Disengage | 6 | OK
5.3 | High Limit Engage | 34 | OK
5.4 | High Limit Disengage | 21 | OK
6 | Resolver Performance | 37 | OK | Variations over 1 turn

## 11359_1
General Information:
Serial num: | 11359
Axis num: | 1
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | Not OK | Lower limit switch lever bent
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | Check | Sqeaking/grinding high pitch noise
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
2.1 | Observations |  | Not OK | Upper limit switch is actuated very close to the "top" of the lever. The axis is almost travling over.
| Motion Performance | µm
3 | Repeatability | 3 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 36 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed.
5. | Switch Performance | µm
5.1 | Low Limit Engage | 17 | OK
5.2 | Low Limit Disengage | 12 | OK
5.3 | High Limit Engage | 171 | Not OK | Limt switch position vs cam wrong. Actuated with to little margin.
5.4 | High Limit Disengage | 11 | OK
6 | Resolver Performance | 37 | OK | Variations over 1 turn

## 11359_2
General Information:
Serial num: | 11359
Axis num: | 2
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | OK
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | Check | Low sqeaking/grinding high pitch noise
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
| Motion Performance | µm
3 | Repeatability | 2 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 30 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed.
5. | Switch Performance | µm
5.1 | Low Limit Engage | 5 | OK
5.2 | Low Limit Disengage | 7 | OK
5.3 | High Limit Engage | 4 | OK
5.4 | High Limit Disengage | 7 | OK
6 | Resolver Performance | 26 | OK | Variations over 1 turn

## 11360_1
General Information:
Serial num: | 11360
Axis num: | 1
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | Check | Some Lemo nuts loose
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | Not OK | Pins offsted one position in lemo connector
1.2.5 | Resolver Sin |  | Not OK | Pins offsted one position in lemo connector
1.2.6 | Resolver Cos |  | Not OK | Pins offsted one position in lemo connector
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations
2.1 | Observations
Motion Performance
3 | Repeatability
4 | Accuracy
5. | Switch Performance
5.1 | Low Limit Engage
5.2 | Low Limit Disengage
5.3 | High Limit Engage
5.4 | High Limit Disengage
6 | Resolver Performance

## 11360_2
General Information:
Serial num: | 11360
Axis num: | 2
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | Check | Some Lemo nuts loose
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | Not OK | Pins offsted one position in lemo connector
1.2.5 | Resolver Sin |  | Not OK | Pins offsted one position in lemo connector
1.2.6 | Resolver Cos |  | Not OK | Pins offsted one position in lemo connector
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations
2.1 | Observations
Motion Performance
3 | Repeatability
4 | Accuracy
5. | Switch Performance
5.1 | Low Limit Engage
5.2 | Low Limit Disengage
5.3 | High Limit Engage
5.4 | High Limit Disengage
6 | Resolver Performance

## 11361_1
General Information:
Serial num: | 11361
Axis num: | 1
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | OK
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
| Motion Performance | µm
3 | Repeatability | 5 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 30 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed.
5. | Switch Performance | µm
5.1 | Low Limit Engage | 6 | OK
5.2 | Low Limit Disengage | 2 | OK
5.3 | High Limit Engage | 19 | OK
5.4 | High Limit Disengage | 11 | OK
6 | Resolver Performance | 3 | OK | Variations over 1 turn

## 11361_2
General Information:
Serial num: | 11361
Axis num: | 2
Test: | Description: | Value | Status: | Comment:
1 | General Inspection
1.1 | Mechanical
1.1.1 | Observations |  | OK
1.2 | Electrical
1.2.1 | Observations |  | OK
1.2.2 | Motor Phase A |  | OK
1.2.3 | Motor Phase B |  | OK
1.2.4 | Resolver Rotor |  | OK
1.2.5 | Resolver Sin |  | OK
1.2.6 | Resolver Cos |  | OK
1.2.7 | Low Limit Switch |  | OK
1.2.8 | High Limit Switch |  | OK
2 | Initial Motion Test
2.1 | Observations |  | OK | Limits very close to mech stops. Readjusted both to get some more margin.
| Motion Performance | µm
3 | Repeatability | 3 | OK | The repeatability is better than the accuracy of the IDL2300 sensor. Measurements with the resolver indicate that the repeatabiulity is in the range of +- 1 micrometer
4 | Accuracy | 36 | OK | Probably accuracy can be even higher if the scalings are tuned vs the IDL2300. Since the requirement is satisfied no futher tuning was perfromed.
5. | Switch Performance | µm
5.1 | Low Limit Engage | 21 | OK
5.2 | Low Limit Disengage | 4 | OK
5.3 | High Limit Engage | 21 | OK
5.4 | High Limit Disengage | 7 | OK
6 | Resolver Performance | 30 | OK | Variations over 1 turn